## Bid Leveling - Summary
Maverick Roof Bid Leveling
Owner | GKI Industrial Minneapolis
Project | 6820 Shingle Creek Pkwy Roof Recover
Location | 6820 Shingle Creek Pkwy, Minneapolis, MN 55430
Bid date | March 30, 2026, 3:00 PM
Area total (SF) | 146000
Template version | 1.0
Category / Item | Unit | Alpha Roofing | Bravo Roofing | Bidder 3 | Bidder 4
Bidder Information
Company |  | Alpha Roofing | Bravo Roofing
Contact |  | Test Contact | Test Contact
Address
City, State, ZIP
Email |  | estimating@alpharoofing.example | estimating@bravoroofing.example
Telephone |  | 555-0100 | 555-0100
License number |  | MN-TEST-001 | MN-TEST-001
Date of bid |  | 2026-03-28 | 2026-03-28
Bid valid until |  | 2026-05-27 | 2026-05-27
Material availability / supply-chain / escalation notes
Project duration (days) |  | 45 | 45
Crew size |  | 8 | 8
Payment terms
Lead time
Single-source manufacturer? (Y/N) |  | Y | Y
Manufacturer selected |  | Test Manufacturer | Test Manufacturer
Company Profile
Annual sales
Net worth
Working capital
Current Dun & Bradstreet rating
Prior Dun & Bradstreet credit appraisal
Years in business / incorporated
Provisions for warranty expense
Insurance coverage
Bonding capacity
Number of offices
Number of employees
ESOP company?
Written safety program?
Drug-tested employees?
Crews dedicated to patch and repair?
Technical services staff
Pre-start meeting with site personnel?
Pricing
Base Bid - Option A | USD | 2100000 | 2050000
Option A - Per SF | USD | 14.3836 | 14.0411
Option A - Wet insulation/deck allowance | USD
Option A - Included alternates | USD
Option A - Total estimate | USD | 2100000 | 2050000
Option A - Contingency | USD
Option A - Grand total | USD | 2100000 | 2050000
Base Bid - Option B | USD | 1980000 | 2010000
Option B - Per SF | USD | 13.5616 | 13.7671
Option B - Wet insulation/deck allowance | USD
Option B - Included alternates | USD
Option B - Total estimate | USD | 1980000 | 2010000
Option B - Contingency | USD
Option B - Grand total | USD | 1980000 | 2010000
20-year contractor workmanship warranty (18-year delta) | USD
Replace skylight with burglar bars; replace curb if required | USD
Scrape, prime and paint roof deck - per SF | USD
Replace wet insulation - per SF | USD
Replace metal roof deck - per SF | USD
Annual preventive maintenance program | USD
Biannual preventive maintenance program - each visit | USD

## Scope Comparison
Scope Inclusion Comparison
Ref. | Item description | Alpha Roofing Include | Alpha Roofing Remark | Bravo Roofing Include | Bravo Roofing Remark | B3 Include | B3 Remark | B4 Include | B4 Remark
1 | Pre-job inspection with building owner | Y |  | Y
2 | Full-time superintendent | Y |  | Y
3 | Contact information sheet | Y |  | Y
4 | Submittals | Y |  | Y
5 | Produce and maintain schedule | Y |  | Y
6 | Phasing and sequencing plan | Y |  | Y
7 | Staging plan | Y |  | Y
8 | New roof drains and assemblies | Y |  | Y
9 | Overflows | Y |  | Y
10 | Scope covers all field areas | Y |  | Y
11 | Pitch pockets | Y |  | Y
12 | Gravel removal | Y |  | Y
13 | 60mil TPO membrane | Y |  | Y
14 | 1-inch ISO | Y |  | Y
15 | Option A: RhinoBond plate/fastener; Option B: mechanically attached plate/fastener | Y |  | Y
16 | Manufacturer periodic inspections | Y |  | Y
17 | Warranty transferable at no cost | Y |  | Y
18 | 20-year TPO manufacturer labor and material NDL warranty | Y |  | Y
19 | 2-year contractor workmanship warranty | Y |  | Y
20 | Condensate-line support / OMG Pipeguards | Y |  | Y
21 | Electrical-line and gas-line support / OMG Pipeguards | Y |  | Y
22 | All MEP-related work required to complete roof project | Y |  | Y
23 | Permits | Y |  | Y
24 | Secure kettles and rooftop equipment | Y |  | Y
25 | Daily site cleaning and proper debris disposal | Y |  | Y
26 | Contractor schedule before work begins | Y |  | Y
27 | Temporary waterproof tie-in at end of each day | Y |  | Y
28 | Completion in accordance with contract documents | Y |  | Y
29 | Protection pads for conduit and free-standing units | Y |  | Y
30 | Protective mat/membrane under existing satellite dishes | Y |  | Y
31 | Metal drip edge into gutter | Y |  | Y
32 | Work completion sign-off | Y |  | Y
33 | Tenant protection and interior debris cleanup | Y |  | Y
34 | Daily site cleanup | Y |  | Y
35 | Final cleanup; deliver blemish-free roof | Y |  | Y
36 | Stack-vent extension per code if required | Y |  | Y
37 | Responsibility for pre-existing structural/skylight/rooftop-equipment conditions | Y |  | Y
38 | Remove abandoned HVAC equipment identified by owner | Y |  | N | Excluded for leveling test
39 | Scrape, prime and paint penetrations, stacks, vents, hatches and curb caps | Y |  | Y
40 | Paint gas lines safety yellow | Y |  | Y
41 | Manufacturer pull test | Y |  | Y
42 | Keep roof free of leaks before commencement | Y |  | Y
43 | Interim site photos and final drone photos | Y |  | Y
44 | Deliver new roof in blemish-free condition | Y |  | Y
45 | TPO walkway pads at roof hatch and major rooftop units | Y |  | Y
46 | Extend RTU condensate lines to drain or gutter system | Y |  | Y

## Import Audit
Import Audit
File | Bidder | Template version | Fields imported | Warnings | Status
Bid_A.xlsx | Alpha Roofing | 1.0 | 69 |  | READY
Bid_B.xlsx | Bravo Roofing | 1.0 | 70 | 1 scope item(s) are excluded | REVIEW